## Slide 1: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
DIGI PROJECT
Migoli-Izazi-Idodi-Kimande
May, 2020

## Slide 2: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Content
Scope of the project.
Hotspot Centers Establishment and Implementation.
Data Collection.
Achievements .
Challenges and Recommendations.

## Slide 3: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Scope of the project.
This study is a part of the project for non discriminating access for Digital Inclusion.
The purpose of the study is to investigate peoples perception on the digital and provision of free digital health education with regards HIV, TB, TSCT.
Study sites; four villages,
two intervention villages (Migoli and Izazi)
two control villages (Idodi and Kimande)

## Slide 4: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Hotspot Centers Establishment and Implementation.
To provide access to digital health information we have established hotspot centers in both intervation villages.
At Migoli Village
We have established hotspot centers at Nyerere High school, Migoli Dispensary, Migoli Village office.
At Izazi Village
We have established Hotspot Centers at Izazi Village Office, and Izazi Dispensary.
Intervention villages Migoli Dispensary and Izazi Dispensary we have Fixed television screens to display offline animations contents with health massages.
Control Villages we have not yet installed hotspot centers, the intention is to limit them with access for health massages for assessment.

## Slide 5: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Scope of Data Collection.
600 Participants, 300 participants from intervention villages and 300 participants from Control villages.
Study visits and data collection exercises
No. Of Visits | Time of Visits | No. Of participants interviewed
1st Visit | April-May 2019 | 600 Participants were interviewed
2nd Visit | August 2019 | 561 Participants were interviewed.
3rd Visit | February 2020 | In-Depth interview (34 Participants were interviewed)
4th Visit | Will be done in June 2020 | We expect to interview 561 or less participants in June 2020

## Slide 6: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Achievements and Lesson learned
We brought free digital health information to communities at Migoli and Izazi.
Communities in the intervention village accepted and uses the hot sport to get free digital health information.
Increase HIV, TB, TSCT awareness in the intervention villages

## Slide 7: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Recommendations and Future work.
Developing sustainability model, for after study hotspot centers sustainability
Connecting the Control villages after last visit of data collection is vital to open access to free health information to the communities.
Progressive community engagement and senthesazation to ensure effective utilisation of health massages contents in the platform.

## Slide 8: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Summary-List of activity already implemented at site.
S/n | Activity
1 | Established 5 hotspot centers for intervation villages
2 | Connecting all 5 Hotspots centers with internet
3 | Training Local Hotsport runners in each center
4. | Advocating to the Local Village leaders on the uses of the DIGI Hotsport platform.
5. | 1ST Field data collection exercise
6 | 2ND Field data collection exercise
7 | In-depth Interview data collection exercise

## Slide 9: FREE ACCESS TO DIGITAL HEALTH INFORMATION IN TANZANIA
Summary-List of activities not yet implemented at site.
S/n | Activity
1 | 4th Follow up to be done in June 2020
2 | Connecting the control Villages, Post June 2020 follow up
3 | Community senthesazation on use of both DIGI Hotspot platforms both Intervation and Control Villages
4 | Developing post June, hotspot centers sustainability plan

## Slide 10: Challenges
COVID 19
Procurement and clearance bureaucracy
Sustainability

## Slide 11
                Thank you